Contract for Karen Palmer – On-site Interviewer

Terms of Contract:

- Must work the term of the contract to receive payment for services

- Employment term starts April 3 and finishes no later than April 14th.

- Employment may end earlier with an early project completion.  Contractors are paid for   the time employed.

- April 3 – set up day

- April 4-14th – interviewing 9am – 9pm, 10 hours with two one hour breaks

- April 3 – set up with VP Marketing Crop Research – Carlo Bianchini

- April 4 – first 4 interviews conducted by Carlo Bianchini as a training aid.  The  remainder of the day Carlo will be overseeing interviews as a training period.

- Jay Thordarson is the on-site project manager.  All on-site needs will be addressed with Jay.

- Jay is responsible for all incentives therefore there will be no handling of participant incentives without his knowledge and approval.

Jay – what have we missed???

Have fun, relax – nothing is that bad!